## Sedex - Web interface
Project name | Sedex - An APP exchange (Download/Upload) product
Assumption
Date | 2015-06-17
Function | Assumption | Note | Estimation (man-day)
Common Tasks |  |  | 8.25
Requirement clarification
Concept (Graphic) Design
HTML Design
Architecture Design |  |  | 3
DB Design |  |  | 1
Environment configuration |  |  | 1.5
Production Deployment |  |  | 1.5
Login |  |  | 1
Logout |  |  | 0.25
Single Sign On (SSO)
System Test |  | 10-15% development effort
System Management |  |  | 0
System config
User Management |  |  | 0
Create/Register New User Account
Edit User
Delete User
View User Info
Search User
Bulk import/update User |  | Import multiple Users into sytem using CSV format. Or update existing User
Role/Right Management |  |  | 0
Manage Users/Partners’ permissions
User Profile Management |  |  | 0
View User Profile
Edit User Profile
Forgot Password
Group Management (Manage User Groups) |  |  | 0
App Management |  |  | 0
Manage App Info |  | App info: - App name, description - App provider - …
Manage App Ratings and Comments
Manage App Price |  | At this moment, all apps are free. But in future, some apps may have prices
Upload App
Download App
Email Function |  |  | 0
Send email to User/Partner when needed
Module 01 |  |  | 0
Total effort (man days) |  |  | 8.25