## Sheet1
Project name | Consentz
Assumption | Estimate is for iPad native application ( ios 7 and onward)
CMS features are included in this estimate
Server/hosting/infrastructure/licenses will be bought the the customer
Task name | Notes/Assumptions | Estimate (man-day)
iOS iPad application |  | 219.5
Database design |  | 5
Architecture design |  | 6
Business analysis |  | 15
Requirement clarification |  | 15
Design UI and mockup |  | 10
Revise mockup after the client feedbacks |  | 2
App navigation design |  | 5
Slide menu |  | 2
Onboarding | Help the user understand the app features at the first time use the app | 3
Login |  | 1
Logout |  | 0.5
Forgot password |  | 0.5
Register new account | Redirect to current sign up page of Consentz | 0.5
Clinic Dash Board | User friendly UI to easily access main features of the app: managing practiioners, view statictics reports.. Etc | 5
Statistic reports | Applying nice animation and UI and showing data on the charts | 7
Managing practioners | Create, update, delete practioners, viewing their detail information | 4
Make appointment | Entering detail patient info and appointment date | 3
Questionaire | A series of YES/NO questions pulling from the server | 4
Patient signature | After fill in information and questionaires, the patient has abity to sign on the app | 1
Taking photo | The app launch the camera to instant photo taken or they can browse from the camera roll | 2
Calendar view | Weekly, monthly view. The doctor/practioners can book in advances for the future months | 7
Full face/body consultation screen | take another picture and draw on it, record the glogau score for wrinkles and also Fitzpatrick scale for skin colour. The side menu will have a menu of : 1. skin quality, 2. Volume loss and 3. Dynamic Wrinkles | 15
Treatment plan | After the consultation, on the treatment plan there will be pre-recorded with each category - eg skin boosters; Suggested 2mls of restylane vital cost £600 to be repeated every 6 months, botox, 3 areas, cost of £400 every 4 months etc | 11
Adding a diary | the treatments can be listed and the practioner can them swipe them into a diary. (ie botox in Jan, Apr, Aug, Filler in Feb and Dec etc..) | 2.5
Sharing treatment plan with patient | This can be shared with the patient so they can see a suggested treatment plan for the year (and cost) and also the receptionist so they can book in appointments the patient wants to make. Assuming sharing here is sending email the party | 1
Make suggestion note | There should also be an opportunity for the doctor to make other suggestions not supported by the pharma (eg Intracel, skin care) and for these too to be added into the annual treatment plan. Needs tick box/ prompts so the practitioner is encouraged to consider offering the full range of products offered by clinic. | 3
Patient follow up a treatment plan | Patient shows interest in treatment but doesn't book - flag to follow up | 2
Consultation note | The doctor can see the old notes and making multiple entries for the same day – can we have multiple entiries on the same day at least being grouped together. | 3
Searching for notes |  | 3
Searching for patients |  | 3
Searching for appointments |  | 3
Medical voice to text | Dictate consultation notes using Dragon - Nuance | 5
Videos/photos to educate patients | about other possible treatments | 2.5
Build up library to deal with photos and drawing |  | 7
Working offline |  | 16
Data synchronization | The app syncs data back to server when it goes online again | 16
Google calendar integration |  | 3
Salesforce integration | Sending data to salesforce via salesforce API | 25
CMS system |  | 77
Architecture design |  | 8
Database design |  | 8
Login |  | 1
Logout |  | 1
Forgot password/change password |  | 1
Reporting | Draft estimate, need to clear what informations we need and what kind of reports the doctor needs to see | 10
APIs for mobile app |  | 20
Searching |  | 5
Referral letter template |  | 3
Mailchim intergration | Including email template design, intergration and testing | 5
Email reminders |  | 2
Content management | Update and manage master contents for the mobile app | 13
Project management |  | 15
Testing | = 15 % development efforts | 44.475
Deployment to production |  | 5
Environment configuration |  | 1
Total effort ( man days ) |  | 361.975

## BSQR3 - COTS Online Booking
Project name | BSQR3 - COTS Online Booking
Assumption | - BSQR3 Proxy Service is available and provides all necessary APIs for COTS Online Booking
CMS features are included in this estimate
Server/hosting/infrastructure/licenses will be bought the the customer
Task name | Notes/Assumptions | Estimate (man-day)
iOS iPad application |  | 219.5
Database design |  | 5
Architecture design |  | 6
Business analysis |  | 15
Requirement clarification |  | 15
Design UI and mockup |  | 10
Revise mockup after the client feedbacks |  | 2
App navigation design |  | 5
Slide menu |  | 2
Onboarding | Help the user understand the app features at the first time use the app | 3
Login |  | 1
Logout |  | 0.5
Forgot password |  | 0.5
Register new account | Redirect to current sign up page of Consentz | 0.5
Clinic Dash Board | User friendly UI to easily access main features of the app: managing practiioners, view statictics reports.. Etc | 5
Statistic reports | Applying nice animation and UI and showing data on the charts | 7
Managing practioners | Create, update, delete practioners, viewing their detail information | 4
Make appointment | Entering detail patient info and appointment date | 3
Questionaire | A series of YES/NO questions pulling from the server | 4
Patient signature | After fill in information and questionaires, the patient has abity to sign on the app | 1
Taking photo | The app launch the camera to instant photo taken or they can browse from the camera roll | 2
Calendar view | Weekly, monthly view. The doctor/practioners can book in advances for the future months | 7
Full face/body consultation screen | take another picture and draw on it, record the glogau score for wrinkles and also Fitzpatrick scale for skin colour. The side menu will have a menu of : 1. skin quality, 2. Volume loss and 3. Dynamic Wrinkles | 15
Treatment plan | After the consultation, on the treatment plan there will be pre-recorded with each category - eg skin boosters; Suggested 2mls of restylane vital cost £600 to be repeated every 6 months, botox, 3 areas, cost of £400 every 4 months etc | 11
Adding a diary | the treatments can be listed and the practioner can them swipe them into a diary. (ie botox in Jan, Apr, Aug, Filler in Feb and Dec etc..) | 2.5
Sharing treatment plan with patient | This can be shared with the patient so they can see a suggested treatment plan for the year (and cost) and also the receptionist so they can book in appointments the patient wants to make. Assuming sharing here is sending email the party | 1
Make suggestion note | There should also be an opportunity for the doctor to make other suggestions not supported by the pharma (eg Intracel, skin care) and for these too to be added into the annual treatment plan. Needs tick box/ prompts so the practitioner is encouraged to consider offering the full range of products offered by clinic. | 3
Patient follow up a treatment plan | Patient shows interest in treatment but doesn't book - flag to follow up | 2
Consultation note | The doctor can see the old notes and making multiple entries for the same day – can we have multiple entiries on the same day at least being grouped together. | 3
Searching for notes |  | 3
Searching for patients |  | 3
Searching for appointments |  | 3
Medical voice to text | Dictate consultation notes using Dragon - Nuance | 5
Videos/photos to educate patients | about other possible treatments | 2.5
Build up library to deal with photos and drawing |  | 7
Working offline |  | 16
Data synchronization | The app syncs data back to server when it goes online again | 16
Google calendar integration |  | 3
Salesforce integration | Sending data to salesforce via salesforce API | 25
CMS system |  | 77
Architecture design |  | 8
Database design |  | 8
Login |  | 1
Logout |  | 1
Forgot password/change password |  | 1
Reporting | Draft estimate, need to clear what informations we need and what kind of reports the doctor needs to see | 10
APIs for mobile app |  | 20
Searching |  | 5
Referral letter template |  | 3
Mailchim intergration | Including email template design, intergration and testing | 5
Email reminders |  | 2
Content management | Update and manage master contents for the mobile app | 13
Project management |  | 15
Testing | = 15 % development efforts | 44.475
Deployment to production |  | 5
Environment configuration |  | 1
Total effort ( man days ) |  | 361.975