## Master
Project name | Sedex - An APP exchange (Download/Upload) product
Assumption | - Server/hosting/infrastructure/licenses (if any) are bought by the customer - Technologies/Frameworks: Java, Spring, Hibernate (DB mapping), MySQL… - System supports Web responsive
Date | 2015-06-17
Effort (man-days)
Web interface | 159
Android
iOS
Windows Phone
Total Effort: | 159

## Sedex - Web interface
|  | Total effort (man days): | 159
Function | Assumption | Note | Estimation (man-day)
Common Tasks/Functions |  |  | 54.75
Requirement clarification |  |  | 8
Concept (Graphic) Design |  |  | 6
HTML Design | Support Web responsive |  | 15
Architecture Design |  |  | 3
DB Design |  |  | 2
Environment configuration |  |  | 2
Production Deployment |  |  | 1.5
Login |  |  | 1
Logout |  |  | 0.25
Single Sign On (SSO) | Intergrate with an existing system |  | 5
Send mail system | Using Java mail library | To send emails to Users/Admin when needed | 5
Performance Test |  |  | 6
System Management |  |  | 3.5
System configuration |  |  | 3
Testing |  |  | 0.5
User Management |  |  | 35
Create/Register New User Account | - User info has 10-20 fields. - User need to confirm his/her registration by clicking on a link in an email | Send email to User after finish | 8
Edit User |  | Can reuse somethings from "Create/Register New User Account" function above | 2.5
Delete User | - Logical delete (just mark as deleted) - Need to delete some relating info: Assigned Roles/Rights/Group… |  | 1.5
View User Info |  |  | 2
Search User | 4-8 search conditions |  | 7
Bulk import/update User |  | Import multiple Users into sytem or update existing User using CSV format. | 6
Assign Users to Group, remove User from Group |  |  | 3
Testing |  |  | 5
Role/Right Management |  |  | 5.75
Manage Users/Partners’ permissions |  |  | 5
Testing |  |  | 0.75
User Profile Management |  |  | 19
Landing Page |  |  | 4.5
View User Profile |  |  | 3
Edit User Profile |  |  | 4
Forgot Password |  | Sending email to User to reset password | 1.5
Manage (Add, List) Favourite Apps |  |  | 3
Testing |  |  | 3
Group Management (Manage User Groups) | - Do not support nested Group (Group in Group) |  | 5.25
Create New Group |  |  | 1.5
View Group Info |  | With number of Users in the Group | 1
Edit Group |  |  | 1
Delete Group | Also delete relating info |  | 1
Testing |  |  | 0.75
App Management |  |  | 29
Upload App |  |  | 5
App Exchange Workflow |  |  | 15
Edit App Info |  | App info: - App name, description - App provider - … | 2
Manage App Ratings and Comments |  |  | 5
Download App | - For Android and iOS apps: Install automatically after download completion - For other apps: User has to manually install after download completion (we will research about "Automatic install App" after download completion later if needed) |  | 8
Search Apps |  | Display Apps by group/categories/search conditions | 4
View App Info (with Ratings/Comments) |  |  | 2.5
Delete App | Also delete relating info |  | 1.5
Testing |  |  | 6
Web-service APIs |  |  | 12
RESTful APIs |  |  | 10
Testing |  |  | 2