## Sedex - Web interface
Project name | Sedex - An APP exchange (Download/Upload) product
Assumption | - Server/hosting/infrastructure/licenses (if any) are bought by the customer - Technologies/Frameworks: Java, Spring, Hibernate (DB mapping), MySQL…
Date | 2015-06-17
|  | Total effort (man days): | 108.25
Function | Assumption | Note | Estimation (man-day)
Common Tasks |  |  | 42.75
Requirement clarification |  |  | 8
Concept (Graphic) Design |  |  | 6
HTML Design |  |  | 8
Architecture Design |  |  | 3
DB Design |  |  | 2
Environment configuration |  |  | 2
Production Deployment |  |  | 1.5
Login |  |  | 1
Logout |  |  | 0.25
Single Sign On (SSO) | We will build a brand-new SSO system, using one of tenologies: JOSSO, CAS... |  | 7
Send mail system | Using Java mail library | To send emails to Users/Admin when needed | 4
System Test |  | 10-15% development effort
System Management |  |  | 3
System configuration |  |  | 3
User Management |  |  | 23
Create/Register New User Account | - User info has 10-20 fields. - User need to confirm his/her registration by clicking on a link in an email | Send email to User after creation | 5
Edit User |  | Can reuse somethings from "Create/Register New User Account" function above | 2
Delete User | - Logical delete (just mark as deleted) - Need to delete some relating info: Assigned Roles/Rights… |  | 1
View User Info |  |  | 1.5
Search User | 4-8 search conditions |  | 5
Bulk import/update User |  | Import multiple Users into sytem or update existing User using CSV format. | 6
Assign Users to Group, remove User from Group |  |  | 2.5
Role/Right Management |  |  | 4
Role/Right Management |  | Manage Users/Partners’ permissions | 4
User Profile Management |  |  | 7.5
View User Profile |  |  | 1
Edit User Profile |  |  | 1.5
Forgot Password |  | Sending email to User to reset password | 1.5
Manage Favourite Apps |  |  | 3.5
Group Management (Manage User Groups) | - Do not support nested Group (Group in Group) |  | 3.25
Create New Group |  |  | 1.5
View Group Info |  | With number of Users in the Group | 0.5
Edit Group |  |  | 1
Delete Group |  |  | 0.25
App Management |  |  | 28
Upload App |  |  | 3
App Exchange Workflow |  |  | 10
Edit App Info |  | App info: - App name, description - App provider - … | 2
Manage App Ratings and Comments |  |  | 5
Manage App Price | At this moment, all apps are free. But in future, some apps may have prices |  | 6
Download App | - For Android apps: Install automatically after download completion - For other apps: User has to manually install after download completion (we will research about "Automatic install App" after download completion later if needed) |  | 7
Search Apps |  | Display Apps by group/categories/search conditions | 4
View App Info (with Ratings/Comments) |  |  | 2.5
Delete App | Also delete relating info |  | 1.5